## Sheet1
Date | Associate Name | Sprint Name | JIRA ID | Story/Task Description | Current Status | ETA | Hours Worked | Incase of Delay, specify reasons | Any Impediments
2020-03-23 | Sarma V | Sprint 1 | DEV-10320 | Return an array of content ids | In Progress |  | 6
2020-04-01 | Praveen M |  |  | Vishwajeet V and Praveen M ADR with Mukul. |  |  | 1
2020-04-01 | Praveen M |  |  | Piping Module Design flow document preparation. | Completed |  | 7
2020-04-02 | Praveen M |  |  | (Holiday)Sri Rama Navami |  |  | 8
2020-04-03 | Praveen M |  |  | Piping module Technical stack Meeting. |  |  | 0.5
2020-04-03 | Praveen M |  |  | Vishwajeet V and Praveen M CD Points with Amit Parse. |  |  | 0.5
2020-04-03 | Praveen M |  |  | Piping Master Postgresql script preparation. |  |  | 7
2020-04-06 | Praveen M |  |  | Piping Module Code Repository - added documents to the repository. |  |  | 1.5
2020-04-06 | Praveen M |  |  | Piping Module discussion with Satya Datla. |  |  | 0.5
2020-04-06 | Praveen M |  |  | Execution of Piping master Create/Insert script. |  |  | 4
2020-04-06 | Praveen M |  |  | Piping Module questions |  |  | 2