## 20200420-20200426
Associate | Sprint | JIRA ID | Story/Task Description | Current Status | Remarks | ETA | Hours Worked | Incase of Delay, specify reasons | Any Impediments
Praveen M | Sprint 1 | PIPE-10001 | 1.Web API a) Logging - Serilog. b) Security - JWT, Password encryption 2. Database Design a) User Management - User, Role, Menu, Actions, QuickLinks b) Organization - Company - Plant, Employee -Department b) Master Data - PipingMaster, Cluster, Corrosion Study, COF, POF, DM c) Transactions - PinpingReport (TML, Confidence, Observations, Recommendations) d) Audit - UserAudit, PipingMasterAudit, PipingReportAudit. | 1.Web API a) Logging - Serilog. Completed b) Security - JWT, Password encryption - In-progress 2. Database Design a) User Management - User, Role, Menu, Actions, QuickLinks. UserAudit. Completed b) Organization - Company - Plant, Employee -Department. Completed c) Master Data - PipeMaster, Documents. Completed d) Master Data - PipeCluster, Corrosion Study, COF, POF, DM, PipeMasterAudit. Yet to start c) Transactions - PinpingReport (TML, Confidence, Observations, Recommendations)Yet to start
Hanumanth G | Sprint 1 | PIPE-10002 | 1. UX Design a) Plant - Fluid page b) Pipe line pages - RBI, Design Data, Internal Corrosion, External Corrosion, Env. Cracking, COF | Completed
Bhargavi G | Sprint 1 | PIPE-10003 | 1. Web APP a) Web App Layout - Header - Logo, Top Menu, LoggedIn User Left - Left Menu, Quick Links Middle - Content | Design Completed
Satya D | Sprint 1 | PIPE-10004 | 1. Web APP a) Login Page b) Forgot Password | Design Completed

## 20200427-20200503
Associate | Sprint | JIRA ID | Story/Task Description | Current Status | Remarks | ETA | Hours Worked | Incase of Delay, specify reasons | Any Impediments
Praveen M | Sprint 1 | PIPE-10005 | 1.Web API a) UserManagemet - API methods. » Register, Login, Logout, ForgotPassword, ResetPassword. b) Master Screen Layout - API methods. » TopMenu, LeftMenu, QuickLinks, UserInfo c) PipeMaster - API methods » Basic Data, Design Data, Internal Corrision, External Corrosion, Environment Cracking, COF, Special DMs » Documents 2. Database Design a) Master - COF, POF-IC, POF-EC, POF-SCC, PipeCluster b) Transactions - PinpingReport (TML, Confidence, Observations, Recommendations) | a) UserManagemet - API methods. Completed » Register, Login, Logout, ForgotPassword, ResetPassword. b) Master Screen Layout - API methods. Completed » TopMenu, LeftMenu, QuickLinks, UserInfo c) PipeMaster - API methods. 10 out of 22 completed, remaining 12 require clarification, sent mail to client » Basic Data, Design Data, Internal Corrision, External Corrosion, Environment Cracking, COF, Special DMs Database Design. a) Master - COF, POF-IC, POF-EC, POF-SCC, PipeCluster. Completed b) Transactions - PinpingReport (TML, Confidence, Observations, Recommendations). Require clarifications, sent a mail to client.
Hanumanth G | Sprint 1 | PIPE-10006 | 1. When clicked on Quick Link - Piping Reports - All reports related to PipeLine should open in Grid(Tabular). Above Reports Grid should have a toolbar with Create ¦ Edit ¦ Copy ¦ View ¦ Print icons. 2. Global search - When Report Number is entered, should be able to open the report. 3. In Inspection priority, should be rounded priotity. 4. Show the full path of Navigation. Parent Plant » Child Plant » Fluid » PipeLine No Ammonia » Ammonia 01 » AL » P01.AL1001 | TO DO
Bhargavi G | Sprint 1 | PIPE-10007 | 1. Web APP a) Web App Master Screen Design » Header - Logo, Top Menu, LoggedIn User » Left - Left Menu, Quick Links b) PipeMaster screen Design » Basic Data, Design Data, Internal Corrision, External Corrosion, Environment Cracking, COF, Special DMs | TO DO
Satya D | Sprint 1 | PIPE-10008 | 1. Web APP a) Login Fields are Username, Password, Login button, Remember Me checkbox, Forgot password link, Logo and Create account link. Default focus on Username. By default Username, Password fields are blank, Remember Me is unchecked. Tab Order - Username, Password, Remember Me, Login, Forgot Password, Create account. Enter/Tab keys aresubstitute for the Login button Username, Password has a valid placeholder Labels(Username, Password) float upward when the text field is in focus or filled. User is able to Login with valid credentials. User is not able to Login with inactive credentials. User is not able to Login with invalid Username or invalid Password. User clicking on browser back button after successful login should not take User to log out mode. User clicking on browser back button after successful logout should not take User to logged in mode. Limit on the total number of unsuccessful login attempts (No. of invalid attempts(3) is configured in BusinessRule Table) Password is in encrypted form when entered. Set Maxlength for Username, Password fields. Text can be pasted in Uername, Password fields. Encrypted characters in “Password” field should not allow deciphering if copied. User should be able to login with the new password after changing the password. User should not be able to login with the old password after changing the password. Spaces should not be allowed before any password characters attempted. Verify the User is still logged in after series of actions such as sign in, close browser and reopen the application. Verify that the timeout of the login session (Session Timeout). Validation message is displayed in case when User leaves Username or Password as blank. User is redirected to home page after successful login. User is redirected to Forgot password page (popup) when clicking on Forgot Password link. User is redirected to Create an account page(popup) when clicking on Create an account link. Logout link(available in Home screen) should redirect to login page. User should enter email or Username to retrieve the password if the User forgets the password, can send password to his email. Security: ============== Verify whether the Passowrd is hashed in Database. Verify whether the login form is revealing any security information by viewing page source Verify that the login page is vulnerable to SQL injection. Verify whether Cross-site scripting (XSS ) vulnerability work on a login page. XSS vulnerability may be used by hackers to bypass access controls. | TO DO

## 20200504-20200510
Associate | Associate | Sprint | JIRA ID | Story/Task Description | Current Status | Remarks | ETA | Hours Worked | Incase of Delay, specify reasons | Any Impediments
Praveen M | Praveen M | Sprint 1 | PIPE-10005 | 1. Web App a) Pipe Master - UI Design b) Plant-Fluid design c)) Pipe Report - UI Design | Got clarifications on Plant-Fluid level screen. Worked on Pipe report design. Worked on Pipe Master -tabs design. Worked on Plant-Fluid screenMatrix and Piping spreasheet design.
Hanumanth G | Hanumanth G | Sprint 1 | PIPE-10006 | 1. Quick Link - Piping Reports - All reports related to PipeLine should open in Grid(Tabular). Above Reports Grid should have a toolbar with Create ¦ Edit ¦ Copy ¦ View ¦ Print icons. 2. Collapsable Menu 3. Quick Link - COF, POF, CML screens
Bhargavi G | Bhargavi G | Sprint 1 | PIPE-10007 | 1. Web APP a) Layout - Bind API methods » Header - Logo, Top Menu, LoggedIn User » Left - Left Menu, Quick Links b) PipeMaster - Design/Bind API methods » Basic Data, Design Data, Internal Corrision, External Corrosion, Environment Cracking, COF, Special DMs c) Pipe Dashboard - Design | Worked on Graphs and Plant-fluid design. Worked on Pipe Master screen design Worked on Master Layout design
Satya D | Satya D | Sprint 1 | PIPE-10008 | PipeMaster - Tabs | TO DO

## 20200511-20200517
Associate | Sprint | JIRA ID | Story/Task Description | Current Status | Remarks | ETA | Hours Worked | Incase of Delay, specify reasons | Any Impediments | Any Impediments
Praveen M | Sprint 1 | PIPE-10005 | 1.Web API a) PipeMaster - API methods » Basic Data, Design Data, Internal Corrision, External Corrosion, Environment Cracking, COF, Special DMs 2. Database Design a) PipeMaster (Additional tables, Additional columns) b) PipeReport (TML, Confidence, Observations, Recommendations, PipeReport) 3. Piping module estimations 4. Understand POF-IC calculation and replicate the same in the PIPING Module. | Worked on Piping module estimations. Understand POF-IC calculation and cnfirmed the SQL SPs can be converted to Postgresql SPs. Made necessary mdifications to Master Layout APIs. Review of Master Layout.
Hanumanth G | Sprint 1 | PIPE-10006 | Pipe Report - Report List with Filter, Report Form design. Flotable Left Menu. Redesign Fluid vs Defect stack chart.
Bhargavi G | Sprint 1 | PIPE-10007 | 1. Web APP a) Layout - Bind Data » Header - Logo, Top Menu, LoggedIn User » Left - Left Menu, Quick Links b) PipeMaster - Bind Data » Internal Corrision, External Corrosion c) Pipe Dashboard - Bind Data. | Integrate API methods to Web App UI » Master Layout - Header » Master Layout - Left Menu » Pipe Master - Basic Tab - Top Left.
Satya D | Sprint 1 | PIPE-10008 | 1. Web App PipeMaster - Basic Data Tab Design Data. Bind data through API calls

## 20200518-20200524
Associate | Sprint | JIRA ID | Story/Task Description | Completed | Remarks | ETA | Hours Worked | Incase of Delay, specify reasons | Any Impediments | Any Impediments
Praveen M | Sprint 1 | PIPE-10005 | 1.Web API a) PipeMaster - API methods » Basic Data, Design Data, Internal Corrision, External Corrosion, Environment Cracking, COF, Trendable DMs, Non-Trendable DMs 2. Database Design a) PipeMaster (Additional tables, Additional columns) b) PipeReport (TML, Confidence, Observations, Recommendations, PipeReport) | Piping Module estimation. Pipe Master » Item navigation Piping Report design. Piping Module design review feedback.
Hanumanth G | Sprint 1 | PIPE-10006 | Global search - Navigation to Pipe Report through UnitNo/ReportNo, Pipe Master through UnitNo. Pipe Report - Report List with Filter, Report Form design. Fluid vs Defect stack chart. Piping Module design Review. Flotable Left Menu. Corrosion Study Page design. | Pipe Report - Report List with Filter, Report Form design. Fluid vs Defect stack chart.
Bhargavi G | Sprint 1 | PIPE-10007 | 1. Web APP a) Layout - Bind Data » Header - Logo, Top Menu, LoggedIn User » Left - Left Menu, Quick Links. » Breadcrumb b) PipeMaster - Bind Data » Basic Data - Grid component » Basic Data - Graph Component » Basic Data - Matrix Component | a) Layout - Bind Data » Header - Logo, Top Menu, LoggedIn User » Left - Left Menu, Quick Links.
Satya D | Sprint 1 | PIPE-10008 | 1. Web App PipeMaster - Design Tab - Top Left section Bind data through API calls

## 20200525-20200531
Associate | Sprint | JIRA ID | Story/Task Description | Current Status | Remarks | ETA | Hours Worked | Incase of Delay, specify reasons | Any Impediments | Any Impediments
Praveen M | Sprint 1 | PIPE-10005 | 1.Web API a) PipeMaster - API methods » Basic Data, Design Data, Internal Corrision, External Corrosion, Environment Cracking, COF, Trendable DMs, Non-Trendable DMs 2. Database Design a) PipeMaster (Additional tables, Additional columns) b) PipeReport (TML, Confidence, Observations, Recommendations, PipeReport) | Report Filter, View List design. Report Add/Edit Form design. Design tables required for POF-IC calculation. Porting of data required for POF-IC calculation. POF-IC update - stored procedure in Postgresql.
Hanumanth G | Sprint 1 | PIPE-10006 | Flotable Left Menu. Corrosion Study Page design. Pipe Master - Add screen design. | Report Add/Edit Form design. Pipe Master - Upload form design.
Bhargavi G | Sprint 1 | PIPE-10007 | 1. Web APP a) PipeMaster - Bind Data » Basic Data - Grid component » Basic Data - Graph Component » Basic Data - Matrix Component | POF-IC Form design. POF-IC calculation API integration.
Satya D | Sprint 1 | PIPE-10008 | 1. Web App PipeMaster - Design Tab - Top Left section Bind data through API calls

## 20200601-20200607
Associate | Sprint | JIRA ID | Story/Task Description | Current Status | Remarks | ETA | Hours Worked | Incase of Delay, specify reasons | Any Impediments | Any Impediments
Praveen M | Sprint 1 | PIPE-10005 | 1.Web API a) POF-IC Calculation. 2. Database Design a) PipeMaster (Additional tables, Additional columns) b) PipeReport (TML, Confidence, Observations, Recommendations, PipeReport) 3. Re-estimate of Piping Module. | Re-estimate of Piping Module.Completed POF-IC stored procedure Completed. Pipe Master - Upload Form design. Completed Database design is pending.
Hanumanth G | Sprint 1 | PIPE-10006 | Corrosion Study Page design. Report Add/Edit Form design. Fluid vs Defect Bubble chart. | Corrosion Study Page design done. Report Add/Edit Form design done. Fluid vs Defect Bubble chart. done
Bhargavi G | Sprint 1 | PIPE-10007 | 1. Web APP a) POF-IC screen API integration b) Pipe Master - Create Form design c) Pipe Master - Edit design tab. | POF-IC screen API integration. Completed Pipe Master - Create Form design. Pending Pipe Master - Edit design tab. Completed
Satya D | Sprint 1 | PIPE-10008 | 1. Web App PipeMaster - Design Tab - Top Left section Bind data through API calls

## 20200608-20200614
Associate | Sprint | JIRA ID | Story/Task Description | Current Status | Remarks | ETA | Hours Worked | Incase of Delay, specify reasons | Any Impediments | Any Impediments
Praveen M | Sprint 1 | PIPE-10005 | 1.Web API a) Pipe Master Create API method. b) Lookup tables Entity creation. Web APP a) Pipe Master - Edit design and Internal corrosion tab. | Lookup Table - Strutural Min Thk lookup. Completed Pipe Master - Add/Edit Basic and Design API methods. Completed Inspection Program - Design. Completed
Hanumanth G | Sprint 1 | PIPE-10006 | Corrosion Study Page redesign. Fluid vs Defect Bubble chart with 10 or more defect codes. | Corrosion Study Page redesign. Completed Fluid vs Defect Bubble chart with 10 or more defect codes. Completed Lookup
Bhargavi G | Sprint 1 | PIPE-10007 | 1. Web APP a) POF-IC screen design b) Pipe Master - Create Form design | a) POF-IC screen design. Completed b) Pipe Master - Create Form design. Completed c) Lookup Table - Strutural Min Thk lookup API integration. Completed
Satya D | Sprint 1 | PIPE-10008 | 1. Web App PipeMaster - Design Tab - Top Left section Lookup Tables Material Codes

## 20200615-20200621
Associate | Sprint | JIRA ID | Story/Task Description | Current Status | Remarks | ETA | Hours Worked | Incase of Delay, specify reasons | Any Impediments | Any Impediments
Praveen M | Sprint 1 | PIPE-10005 | 1.Web API a) Pipe Master - Edit IC, EC API method. b) Lookup tables API methods - Material Codes | a) Pipe Master - Edit IC, EC API method. Completed b) Lookup tables API methods - Material Codes. Completed
Bhargavi G | Sprint 1 | PIPE-10007 | 1. Web APP a) Pipe Master - Edit IC, EC API integration. b) POF-IC/EC View API integration. | a) Pipe Master - Edit IC, EC API integration. Completed b) POF-IC/EC View API integration. Completed
Satya D | Sprint 1 | PIPE-10008 | 1. Web App a) Lookup Tables - Material Codes

## 20200622-2020028
Associate | Sprint | JIRA ID | Story/Task Description | Current Status | Remarks | ETA | Hours Worked | Incase of Delay, specify reasons | Any Impediments | Any Impediments
Praveen M | Sprint 1 | PIPE-10005 | 1.Web API a) Pipe Master - Add/Edit Design, IC and EC changes. b) Pipe Report API methods c) POF IC/EC Calculation . | a) Pipe Master - Add/Edit Design, IC and EC changes. Completed b) Pipe Report API methods. Completed c) POF IC/EC Calculation . POF-IC Completed POF-EC calculation is not sent by Client
Bhargavi G | Sprint 1 | PIPE-10007 | 1. Web APP a) Pipe Master Add/Edit- User input fields, auto data pickup fields and calculation fields and make in separate blocks. b) Pipe Report design. | a) Pipe Master Add/Edit- User input fields, auto data pickup fields and calculation fields and make in separate blocks. Design Tab is Completed b) Pipe Report design. Pipe Report Add Completed
Satya D | Sprint 1 | PIPE-10008 | 1. Web App a) Lookup Tables - Material Codes

## 20200629-20200705
Associate | Sprint | JIRA ID | Story/Task Description | Current Status | Remarks | ETA | Hours Worked | Incase of Delay, specify reasons | Any Impediments | Any Impediments
Praveen M | Sprint 1 | PIPE-10005 | 1.Web API a) Pipe Report API methods - Changes b) POF EC Calculation. | 1.Web API a) Pipe Report API methods - Changes (View/Add/Edit API methods). Completed b) POF EC Calculation. (Master Tables for EC - ExternalCorrosion Rate, CUI Corrosion Rate, External Suceptability, CUI Suceptability) Completed (sent a mail) 2. Web APP a) Pipe Master - Edit Basic, Design, IC and EC changes. (Segregation of User Input, Auto Pick, Calculated fields). Completed
Bhargavi G | Sprint 1 | PIPE-10007 | 1. Web APP a) Pipe Report VIEW/ADD/EDIT API Integration. B) Pipe Report UI Feedback changes. | 1. Web APP a) Pipe Report VIEW/ADD/EDIT API Integration. B) Pipe Report UI Feedback changes. Completed (Sent a mail)
Satya D | Sprint 1 | PIPE-10008 | 1. Web App a) Lookup Tables - Material Codes

## 20200706-20200712
Associate | Sprint | JIRA ID | Story/Task Description | Current Status | Remarks | ETA | Hours Worked | Incase of Delay, specify reasons | Any Impediments | Any Impediments
Praveen M | Sprint 1 | PIPE-10005 | 1.Web API a) Corrosion study Field mapping. b) POF CUI calculation. 2. Web App a) Corrosion Study design. | 1. Web API a) Corrosion study Field mapping. Completed. 2. Web APP a) Corrosion Study design. Completed.
Bhargavi G | Sprint 1 | PIPE-10007 | 1. Web APP a) Pipe Report VIEW/ADD/EDIT API Integration. b) Pipe Report Print/Upload documents. | 1. Web APP a) Pipe Report VIEW/ADD/EDIT API Integration. In-Progress
Satya D | Sprint 1 | PIPE-10008 | 1. Web App a) Lookup Tables - Material Codes

## Sheet1
Associate | Sprint | JIRA ID | Story/Task Description | Current Status | Remarks | ETA | Hours Worked | Incase of Delay, specify reasons | Any Impediments | Any Impediments
Praveen M | Sprint 1 | PIPE-10005 | 1.Web API a) Corrosion study feedback. b) What IF Analysis Field Mapping. c) POF CUI calculation. 2. Web App a) What IF Analysis design.
Bhargavi G | Sprint 1 | PIPE-10007 | 1. Web APP a) Pipe Report VIEW/ADD/EDIT API Integration. b) Corrosion Study API Integration.
Satya D | Sprint 1 | PIPE-10008 | 1. Web App a) Lookup Tables - Material Codes